Version <1.0>

Revision History

|  |  |  |  |
| --- | --- | --- | --- |
| **Date** | **Version** | **Description** | **Author** |
| <dd/mmm/yy> | <x.x> | <details> | <name> |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |

Table of Contents

[1. Introduction 4](#_Toc413446305)

[2. Project Overview 4](#_Toc413446306)

[2.1 Project Purpose, Scope, and Objectives 4](#_Toc413446307)

[2.2 Assumptions and Constraints 4](#_Toc413446308)

[2.3 Project Deliverables 4](#_Toc413446309)

[3. Project Organization 4](#_Toc413446310)

[3.1 Organizational Structure 4](#_Toc413446311)

[3.2 Roles and Responsibilities 4](#_Toc413446312)

[4. Management Process 4](#_Toc413446313)

[4.1 Project Estimates 4](#_Toc413446314)

[4.2 Project Plan 4](#_Toc413446315)

[4.2.1 Phase and Iteration Plan 5](#_Toc413446316)

[4.2.2 Releases 5](#_Toc413446317)

[4.2.3 Project Schedule 5](#_Toc413446318)

[4.2.4 Project Resourcing 5](#_Toc413446319)

[4.3 Project Monitoring and Control 5](#_Toc413446320)

[4.3.1 Reporting 5](#_Toc413446321)

[4.3.2 Risk Management 5](#_Toc413446322)

[4.3.3 Configuration Management 6](#_Toc413446323)

# Introduction

* This software develop plan is used to illustrate a series of development activities of Team 4 in term of phases and iterations to implement an application called EverRun.
* The detail information of each iterations is given in the Iteration Plans.

# Project Overview

## Project Purpose, Scope, and Objectives

* The purpose of this project is to create a friendly, easy-to-approach environment to encourage people to get outside and walk more.
* Users can have a cute pet to raise by earning rewards from walking and they can share their achievement records on facebook as well.
* An android application which contains Unity3d and Java code implementation will be supply at the end of the semester.

## Assumptions and Constraints

* Project has a fixed schedule of 7 weeks to release.
* The integration of unity and android studio must be finished in the 4th week.
* All the members have an ability to implement java programming language on Android Studio.
* No budget supplied.
* Project has 5 people, and no more people will be added during the project.

## Project Deliverables

A list of the artifacts will be created during the project:

* UML use case diagram for game design
* Class diagrams
* Design Story
* Project Plan
* User Interface Prototype
* Database Design
* Test Cases
* Software Architecture Document
* Implementation release
* Vision Document
* The target delivery dates for the end of each phases:

|  |  |
| --- | --- |
| **Phase** | **Target Date** |
| Inception | October 29, 2017 |
| Elaboration | November 4, 2017 |
| Construction Iteration 1 | November 11, 2017 |
| Construction Iteration 2 | November 25, 2017 |
| Construction Iteration 3 | December 11, 2017 |
| Transition | December 18, 2017 |

# Project Organization

## Organizational Structure

## Roles and Responsibilities

|  |  |
| --- | --- |
| **Person, Role** | **Responsibility** |
| Tran Thoai Thong, Designer, Implementer  Ho Sy Nguyen, Designer, Implementer  Le Duy Bach, Implementer, Tester  Bui Nguyen Duc Toan, Implementer, Business Analyst  Lieng The Phy, Tester, Business Analyst | Class diagram designer and Unity code developing  UI designer and Unity code developing  Android and its integration with Unity developing and testing  Android code developing, helping in content and features creating  Testing Unity code function, content and features creating |

# Management Process

## Project Estimates

[Provide the estimated cost and schedule for the project, as well as the basis for those estimates, and the points and circumstances in the project when re-estimation will occur.]

## Project Plan

### Phase and Iteration Plan

This project is going to be conducted using the The Rational Unified Process Model. In this model, multiple iterations occur in the same time. The table below shows the estimated timeline for this project.

|  |  |  |  |
| --- | --- | --- | --- |
| Phase | No of Iterations | Begin | End |
| Inception Phase | 2 | Week 1 | Week 2 |
| Elaboration Phase | 3 | Week 3 | Week 4 |
| Construction Phase | 3 | Week 5 | Week 9 |
| Transition Phase | 2 | Week 10 | Week 10 |

Table 4.2.1a Timeline for each phase of the process

|  |  |  |
| --- | --- | --- |
| Phase | Description | Milestone |
| Inception Phase | Decide the Goal of this Project. Evaluate resources and risks. Researches on free technologies. | -Decide to keep the goal or not. The Go/No Go Decision for this project. |
| Elaboration Phase | Build the architecture of the project.  Research and build test on some feature  Design the UI and learn how to build it.  Testing before deciding which tool to use.  Risk and human resources management | -Have a clear vision how to do each task in the Construction Phase.  - Decide a suitable tool to do different section.  - Clear vision on how the final software works and looks like. |
| Construction Phase | Create Assets and UI  Code features.  Testing | -Full features achieved planned in previous phase  -No bug in the software  -Avoid risks. |
| Transition Phase | Widely Test  Fixing Issues  Finish all features  Wrap up the project, reviewing the work and learning from mistakes | -Testing and have good feedbacks  -Response all feedbacks before deadline.  -Each review each other work, learn from their mistakes for future works. |

Table 4.2.1b Detailed description and goal for each phase

### Releases

A demo is going to be released at the end of week 9. This demo is released for testing, and the testers are the students of class CS300.

The final version is going to be released at the end of week 10. It will be the final submission of this project.

### Project Schedule

## Project Monitoring and Control

### Reporting

[Provide approaches to reporting project status. Approaches may include

* Weekly meeting
* Weekly status report
* Informal chats]

### Risk Management

[Identify risks in your project. The risks should be prioritized, and shorted according to their priority.]

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Risk ID | Risk Description | Probability | Impact | Priority | Mitigation Strategy or Contingency Plan |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |

### Configuration Management

[Determine tools to be used for storage and sharing source code and files. Tools can be used, such as:

* Google drive or Dropbox, etc. for storing and sharing documents and files.
* Git, Bitbucket, etc. for managing source code and related files

]