EverDoggo

Software Development Plan

Version <1.0>

Revision History

|  |  |  |  |
| --- | --- | --- | --- |
| **Date** | **Version** | **Description** | **Author** |
| <dd/mmm/yy> | <x.x> | <details> | <name> |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |

Table of Contents

[1. Introduction 4](#_Toc413446305)

[2. Project Overview 4](#_Toc413446306)

[2.1 Project Purpose, Scope, and Objectives 4](#_Toc413446307)

[2.2 Assumptions and Constraints 4](#_Toc413446308)

[2.3 Project Deliverables 4](#_Toc413446309)

[3. Project Organization 4](#_Toc413446310)

[3.1 Organizational Structure 4](#_Toc413446311)

[3.2 Roles and Responsibilities 4](#_Toc413446312)

[4. Management Process 4](#_Toc413446313)

[4.1 Project Estimates 4](#_Toc413446314)

[4.2 Project Plan 4](#_Toc413446315)

[4.2.1 Phase and Iteration Plan 5](#_Toc413446316)

[4.2.2 Releases 5](#_Toc413446317)

[4.2.3 Project Schedule 5](#_Toc413446318)

[4.2.4 Project Resourcing 5](#_Toc413446319)

[4.3 Project Monitoring and Control 5](#_Toc413446320)

[4.3.1 Reporting 5](#_Toc413446321)

[4.3.2 Risk Management 5](#_Toc413446322)

[4.3.3 Configuration Management 6](#_Toc413446323)

Software Development Plan

# 

# Introduction

* This software develop plan is used to illustrate a series of development activities of Team 4 in term of phases and iterations to implement an application called EverRun.
* The detail information of each iterations is given in the Iteration Plans.

# Project Overview

## Project Purpose, Scope, and Objectives

* The purpose of this project is to create a friendly, easy-to-approach environment to encourage people to get outside and walk more.
* Users can have a cute pet to raise by earning rewards from walking and they can share their achievement records on facebook as well.
* An android application which contains Unity3d and Java code implementation will be supply at the end of the semester.

## Assumptions and Constraints

* Project has a fixed schedule of 7 weeks to release.
* The integration of unity and android studio must be finished in the 4th week.
* All the members have an ability to implement java programming language on Android Studio.
* No budget supplied.
* Project has 5 people, and no more people will be added during the project.

## Project Deliverables

A list of the artifacts will be created during the project:

* UML use case diagram for game design
* Class diagrams
* Design Story
* Project Plan
* User Interface Prototype
* Database Design
* Test Cases
* Software Architecture Document
* Implementation release
* Vision Document
* The target delivery dates for the end of each phases:

|  |  |
| --- | --- |
| **Phase** | **Target Date** |
| Inception | October 29, 2017 |
| Elaboration | November 4, 2017 |
| Construction Iteration 1 | November 11, 2017 |
| Construction Iteration 2 | November 25, 2017 |
| Construction Iteration 3 | December 11, 2017 |
| Transition | December 18, 2017 |

# Project Organization

## Organizational Structure

[Describe the organizational structure of the project team, including management and other review authorities.

Example,

]

## Roles and Responsibilities

[Identify the project organizational units that will be responsible for each of the disciplines, workflow details, and supporting processes. The text below is provided as an example.

Refer to the lecture note “Week 2 – Project Assignments” for predefined roles and responsibilities.

]

|  |  |
| --- | --- |
| **Person** | **Role** |
| Susan Snow, Business Analyst  Henry Halfpipe, Tester  TBD1, Developer  TBD2, Team leader |  |

# Management Process

## Project Estimates

[Provide the estimated cost and schedule for the project, as well as the basis for those estimates, and the points and circumstances in the project when re-estimation will occur.]

## Project Plan

[This section contains the schedule and resources for the project.]

### Phase and Iteration Plan

[Specify how many phases of the project. Each phase should include starting date, ending date, phase name, and overall objectives.

Refer to the lecture note “LN04 -- Project Assignments”, slides #1 and #11 for the initial plan.

List iterations and the objectives to be accomplished for each of the iterations.]

It is OK to include:

 Work Breakdown Structure (WBS)

 a timeline or Gantt chart showing the allocation of time to the project phases and iterations

 identify major milestones with their achievement criteria

Define any important release points and demos.

### Releases

[A brief description of each software release and whether it’s demo, beta, and so on.]

### Project Schedule

[Diagrams or tables showing target dates for completion of iterations and phases, release points, demos, and other milestones.

MS project schedule can be copied here]

## Project Monitoring and Control

### Reporting

[Provide approaches to reporting project status. Approaches may include

* Weekly meeting
* Weekly status report
* Informal chats]

### Risk Management

[Identify risks in your project. The risks should be prioritized, and shorted according to their priority.]

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Risk ID | Risk Description | Probability | Impact | Priority | Mitigation Strategy or Contingency Plan |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |

### Configuration Management

[Determine tools to be used for storage and sharing source code and files. Tools can be used, such as:

* Google drive or Dropbox, etc. for storing and sharing documents and files.
* Git, Bitbucket, etc. for managing source code and related files

]